## Sheet1
project	task	planned_start	planned_finish	actual_start	actual_current	actual_finish
symphony	launch team	10 January 2017	20 January 2017	12 January 2017	23 January 2017	24 January 2017
symphony	create model	21 January 2017	15 February 2017	23 January 2017	13 February 2017	13 February 2017
ordertocash	launch team	11 January 2017	22 January 2017	13 January 2017	21 January 2017	21 January 2017
ordertocash	create model	15 January 2017	25 January 2017	17 January 2017	22 January 2017	22 January 2017
ordertocash	create kpis	19 January 2017	3 March 2017	17 January 2017	27 February 2017	27 February 2017
ordertocash	create analytics	26 January 2017	25 February 2017	26 January 2017	13 February 2017
ordertocash	manage process	3 February 2017	7 March 2017	6 February 2017	10 February 2017
ordertocash	review project	8 February 2017	1 April 2017